## Duty Roster
Name
Personal
2 water bottles or 1 & a | X | X | X | X | X | X | X
camel back | X | X | X | X | X | X | X
large water containers | X | X | X | X | X | X | X
clothes, etc. | X | X | X | X | X | X | X
Patrol Gear
stoves (3) |  |  | X |  | X |  | X
gas/fuel | * |  | X |  | X |  | X
big pot set |  | X
spatula & large spoon |  | X
dining fly
bio degradable soap |  |  |  | X
scrubbing pad |  |  |  | X
food & garbage bags | X | X | X | X | X | X | X
water filter |  |  |  | X
iodine |  | X
large 1st aid kit |  | X
trowel (optional) | [6 empty] | X
tent/tarps |  |  | all 4 bring 1 each
own breakfasts & lunches
Meals To Carry | Dinner 1 | Dinner 5 | trash out | Dinner 3 | trash out | Dinner 4 | Dinner 2
Duties
Make Dinner 1 | 1 | 1
Make Dinner 2 | 1 | [5 empty] | 1
Make Dinner 3 |  |  | 1 | 1
Make Dinner 4 |  |  |  |  | 1 | 1
Make Dinner 5 |  | 1 |  |  |  |  | 1
Clean Up 1 |  |  | 1 | 1
Clean Up 2 |  |  |  |  | 1 | 1
Clean Up 3 | 1 | [5 empty] | 1
Clean Up 4 |  | 1 | 1
Clean Up 5 | 1 |  |  |  | 1
pump water 1 |  |  |  |  | 1 |  | 1
pump water 2 |  | 1 | 1
pump water 3 |  |  |  |  | 1 | 1
pump water 4 | 1 |  |  | 1
pump water 5 |  |  | 1 | 1
Eat w/hares 1 | [5 empty] | 1
Eat w/hares 2 |  |  |  | 1
Eat w/hares 3 |  | 1
Eat w/hares 4 | [6 empty] | 1
Eat w/hares 5 | [5 empty] | 1
* carry 1/2 propane fuel from Wed

## Menus & Shopping list
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | TASKS
| 2007-08-14 | 2007-08-15 | 2007-08-16 | 2007-08-17 | 2007-08-18 | 2007-08-19 | Misc Calls and To Do
Breakfast | TakeEarliest ferry | Bring your own | Bring your own | Bring your own | Bring your own | Bring your own |  | equipment check list
| Eat at home | [6 empty] | call Ralph re combination
| Bring a snack |  |  | up really early |  | up really early & out |  | go check food in locker
call Will Li for dried cheese cake
Service project ranger calls
Lunch | bag lunch | [6 empty] | Call Kathy at church to ensure we have the basement
| money | Bring your own | Bring your own | Bring your own | Bring your own | Bring your own | List to people:
[6 empty] | bring money for drive home |  | Bring own trail breakfasts
Bring own trail lunches
Dinner | burgers | spaghetti | Chicken in a bag w/ | FD - TBD | FD - TBD |  |  | lots of water
| buns | sauce | rice a roni | mashed potatoes | zataranes
| tomatoes | bag salad w/dressing | dried veges | dried veges | dried veges |  | Agenda for training weekend
| lettuce | parmesan | soup |  |  |  |  | lunches
| onion | garlic bread | [5 empty] | water
shoes
trail etiquite
| lemonade | tang | lemonade | tang | lemonade |  |  | hand out check list
| pudding | pudding | pudding | dried cheese cake | pudding |  | Pack inspection (at Church, call Kathy - above)
| milk | milk | milk | milk | milk |  |  | Fix date
remind people
Make up check list
| 1st Tuesday am ferry leaves at 5:45, we need to be there by 5:15, transit time is 25 minutes so we leave the church at 4:50 am | [6 empty] | make sure they have check list
| Costco | QFC | Whole Foods | perishable |  |  | Payment
| burger | puding (4) | milk | tomatoes | Matt Wilson | Teddy Pickard |  | Collect the last $60
| buns | rice a roni | yogurts (2) | lettuce | Nick Millman | Chris Millman |  | Use event to get it
| lemonade (3) | dried soup | flax oil | onion | Kenny Mentele | Tommy Colligan
| milkman (5) | zataranes | dried veges? (3) | bag salad w/dressing | Sunny Temple | Zach Bryant | Transportation
| pasta |  |  | garlic bread | PJ Prins | Bill Pickard | x | Ferry schedule
| spaghetti sauce |  |  |  | Stephan Skalbania | Ed Millman |  | Shuttle arrangement
| tang (2) |  |  |  | Trevor Robinson |  |  | ferry schedule
| mashed potatoes |  |  |  | Thomas Hollowell |  |  | tour permit
Bill Sloan
[5 empty] | Ralph Prins |  | Pre trip
|  |  | Other |  |  |  |  | dehydrate tomato sauce
Chicken in a bag
dried veges?
dried cheese cake?
Outdoor & More, etc.
Freeze dried din 1
Freeze dried din 2
Formulas:
Day 2 = [Day 1]+1
Day 3 = [Day 2]+1
Day 4 = [Day 3]+1
Day 5 = [Day 4]+1
Day 6 = [Day 5]+1

## Gantt Chart
Line No | Task description | Responsibility | Time | 2007-06-30 | 2007-07-01 | 2007-07-02 | 2007-07-03 | 2007-07-04 | 2007-07-05 | 2007-07-06 | 2007-07-07 | 2007-07-08 | 2007-07-09 | 2007-07-10 | 2007-07-11 | 2007-07-12 | 2007-07-13 | 2007-07-14 | 2007-07-15 | 2007-07-16 | 2007-07-17 | 2007-07-18 | 2007-07-19 | 2007-07-20 | 2007-07-21 | 2007-07-22 | 2007-07-23 | 2007-07-24 | 2007-07-25 | 2007-07-26 | 2007-07-27 | 2007-07-28 | 2007-07-29 | 2007-07-30 | 2007-07-31 | 2007-08-01 | 2007-08-02 | 2007-08-03 | 2007-08-04 | 2007-08-05 | 2007-08-06 | 2007-08-07 | 2007-08-08 | 2007-08-09 | 2007-08-10 | 2007-08-11 | 2007-08-12 | 2007-08-13 | 2007-08-14 | 2007-08-15 | 2007-08-16 | 2007-08-17 | 2007-08-18 | 2007-08-19 | 2007-08-20 | 2007-08-21 | Practices Hikes | 2007-06-30 | 7/8/2007 (Parsons) | 2007-07-15 | 2007-07-22 | 2007-07-29 | 2007-08-05 | 2007-08-12 | Must do at least this many trips | Plan to do this many trips | Done
1 | Practice hikes | Bill | [54 empty] | #REF! | 1 | - | 1 | - | 1 | 1 | 1 | 4 | 5
2 | Fill out schedual | Bill and matt | [54 empty] | #REF! | 1 | - | [5 empty] | 4 | 1
3 | Groups | Matt | done | [53 empty] | #REF! | 1 | - | [5 empty] | 4 | 1
4 | Reservations | Bill | done | [53 empty] | #REF! | - | - | [5 empty] | 4 | 0
5 | Menu | Matt | done | [54 empty] | - | ? |  |  | 1 |  |  | 4 | 1
6 | Shopping list | Matt | done | [53 empty] | #REF! | - | - | [5 empty] | 4 | 0
7 | close off registration (call John) | Bill | 2007-07-21 | [53 empty] | #REF! | 1 | - | [5 empty] | 2 | 1
8 | revised budget | Matt | 2007-07-21 | [53 empty] | #REF! | 1 | - | [5 empty] | 3 | 1
9 | spelling | Matt | 2007-07-21 | [53 empty] | #REF! | - | - | [5 empty] | 3 | 0
10 | receive permits from NPS | Ralph/Bill | 2007-07-21 | [53 empty] | #REF! | - | [6 empty] | 3 | 0
11 | equipment lists | Matt | 2007-07-22 | [21 empty] | We are here | [31 empty] | #REF! | - | - | [5 empty] | 2 | 0
12 | Send e-mail to all | Matt | 2007-07-22
13 | Integrate to do list into this list | Matt | 2007-07-22
14 | transportation | Bill | 2007-07-27 | [53 empty] | #REF! | - | - | [5 empty] | 2 | 0
15 | tour permit | Bill | 2007-07-27 | [53 empty] | #REF! | - | - | [5 empty] | 2 | 0
16 | Parking Plans | Bill and Ed, or ralhp | 2007-07-27 | [53 empty] | #REF! | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 7
17 | Payment - budget $120, pay $60 | Everyone | 2007-08-05 | [53 empty] | #REF! | 1
18 | Send in final payment no later than | Everyone | 2007-08-05 | [53 empty] | #REF!
19 | Group meeting | Matt/group | 2007-08-05 | [53 empty] | #REF! | -
20 | Make chart for who carries | Matt | 2007-08-05 | [53 empty] | #REF!
21 | Appoint Historian and Photographer | Matt | 2007-08-05 | [53 empty] | #REF!
22 | several days to shop | Matt and Bill | 2007-08-06 | [53 empty] | Total | 7 | 1 | 2 | 1 | 3 | 2 | 2
23 | itineraries | Bill | 2007-08-07
24 | Meeting:pack | Everyone | 2007-08-08 | [53 empty] | Matt, call and fill in the chart for commitments for the boys - dates and numbers to match. They can count their own hikes, but they need to understand that they should be at least 8 miles, significant hill component, and done with a minimum 40 lb pack. For anyone with a 'must do of 3 or 4, at least one of them needs to be done with me.
25 | Check gear night | Everyone | 2007-08-08
26 | leave-behind bulletin | Bill | 2007-08-10
27 | car checks | Drivers | 2007-08-10
28 | Meeting:packing food | Everyone | 2007-08-12
29 | Buy perishables & last minute stuff | Bill | 2007-08-13
30 | Drive | all | 2007-08-14
31 | Pick up permits | Leaders of groups | 2007-08-14
32 | hike - by day - | all | 2007-08-15
33 | Historian's report | Historian | 2007-08-21
34 | Settle up budget & report | Bill | 2007-08-21
35
36
37
38
39
40
41
42